## Sheet1
Task ID | Task | Start Week | Duration (Weeks) | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11
1 | Project Problem IdentificTION | 1 | 1 | bar: Week 1
2 | Git and development environment setup | 1 | 1 | bar: Week 1
3 | Product backlog creation | 2 | 1 | bar: Week 2
4 | Project proposal and risk analysis | 3 | 1 | bar: Week 3
5 | Requirement and use case modelling | 4 | 1 | bar: Week 4
6 | Class and sequence diagrams | 5 | 1 | bar: Week 5
7 | Architectural design | 6 | 1 | bar: Week 6
8 | Design pattern implementation | 7 | 1 | bar: Week 7
9 | Coding and unit testing | 8 | 1 | bar: Week 8
10 | Automated testing with Github Action | 9 | 1 | bar: Week 9
11 | Sprint planning and task review | 10 | 1 | bar: Week 10
12 | Final integration, documentation and presentation | 11 | 1 | bar: Week 11